## Brief
1 Purpose
This brief presents eagle view of the Excel tracker to plan, execute, and report hardware‑to‑software engineering sprints.
2 Quick‑Start Workflow
· Exclusive README available in the tracker for detailed Glossary
· Map Objectives & Epics in OKR_Epic_Map. Track % complete as stories close.
· During Sprint Planning fill Sprint_Backlog with GitHub Story_IDs, story points, owners.
· Break each story into actionable items in Task_Board (Task_ID = sub‑issue ID).
· Log defects in Defect_Log; update status and closure dates.
· At sprint close, record committed / completed points in Velocity_Data and daily remaining in Burndown_Template. Dashboards refresh automatically.
3 Tracker Cheat‑Sheet :
Sheet | Role
README | Detailed glossary and steps
OKR_Epic_Map | Strategic alignment – one row per epic with OKR linkage.
Sprint_Backlog | Sprint plan – story‑level scope, size, ownership.
Task_Board | Granular task tracking beneath each story.
Velocity_Data | Velocity inputs – committed vs completed per sprint.
Burndown_Template | Daily remaining story‑points (feeds burndown chart).
Defect_Log | Bug lifecycle with severity & MTTR.
Sprint_Overview | Narrative focus for each sprint.
Dashboard | Auto‑generated charts & KPIs.
4 Dashboard Optics
· Sprint Velocity – throughput trend.
· Sprint Burndown – plan vs actual inside the sprint.
· Defect Trend – new vs closed bugs per sprint.
· Epic Completion Pie – portfolio progress across epics.
5 Conventions & Tips
· Story_ID and Task_ID link to GitHub Issue numbers – one source of truth.
· Use a consistent story‑point scale.
· Update the tracker before daily stand‑up to keep charts current.
· Archive old sprints to a new workbook annually.
6 Project Execution
· S/W Architecture – UML Diagrams - https://plantuml.com/
· H/W Architecture – www.wokwi.com
· 1 Story Point Equals 1 Day Effort of 1 Associate
· Tasks to be Added and maintained in github
· The Same Tasks will be maintained as Stories in Agile Tracker
· Bugs to be Added and maintained using Issues feature of github.
· The same will be maintained as Defects in Agile Tracker
· Agile Workflow – Use this Agile Tracker

## README
Step | Notes
1. Fill OKR_Epic_Map first | Align each Epic to OKRs
2. During Sprint Planning, populate Sprint_Backlog | Size Story_Points and assign Owner
3. Break Stories into discrete Tasks in Task_Board | Use checkbox (TRUE/FALSE) in Done column for burndown accuracy
4. Log discovered defects in Defect_Log | Capture severity & MTTR for quality optics
5. At end of sprint, update Velocity_Data | Copy committed vs completed numbers here
6. Dashboard updates automatically via formulas and chart | Velocity chart plots trend across sprints
Sheet | Field / Column | Definition / Notes
OKR_Epic_Map | Objective | Strategic, qualitative goal the epic advances
| Key Result | Quantifiable outcome used to measure Objective success
| Epic Name | ZenHub Epic title (links multiple stories)
| Epic Owner | Single accountable person for the epic
| Target Release | Planned semantic-version or milestone (e.g., v1.2)
| Status (%) | Percent complete (roll-up of story progress)
| Comments | Risks, dependencies, or helpful links
Sprint_Backlog | Sprint_ID | Integer sprint label (1, 2, …) matching Velocity_Data
| Story_ID | GitHub Issue # for the user story (acts as unique key)
| Story_Title | Concise summary of behaviour/value
| Epic | Parent Epic Name (must match OKR_Epic_Map.Epic Name)
| Story_Points | Relative estimate (e.g., Fibonacci 1‑13)
| Owner | Primary engineer responsible for delivery
| Status | Pipeline state (Todo / In Progress / Review / Done)
| Start_Date | Actual date work begins (yyyy‑mm‑dd)
| End_Date | Planned finish date
| Days_Remaining | Formula: End_Date − TODAY()
| Percent_Complete | % checklist items done or status‑based rule
Task_Board | Sprint_ID | Sprint number for quick filtering
| Story_ID | Parent Story’s GitHub Issue #
| Task_ID | GitHub Issue or Task‑list item ID representing sub‑task
| Task_Description | Actionable development activity
| Owner | Engineer owning this task (can differ from Story Owner)
| Status | Todo / In Progress / Blocked / Done
| Start_Date | Date task work begins
| End_Date | Actual completion date
Velocity_Data | Sprint_ID | Sprint label (syncs with Sprint_Backlog)
| Story_Points_Committed | Sum of points pulled into sprint at planning
| Story_Points_Completed | Sum of points accepted as Done at sprint end
Burndown_Template | Day | Sequential day # within the sprint
| Planned_Remaining | Ideal remaining story points each day (straight‑line)
| Actual_Remaining | Real remaining story points at day‑end
Defect_Log | Defect_ID | GitHub Issue # with 'bug' label or internal defect tracker ID
| Summary | Short description of the defect
| Severity (1‑5) | 1=Critical, 5=Minor cosmetic
| Sprint_Found | Sprint_ID when defect discovered
| Sprint_Fixed | Sprint_ID when defect resolved
| Status | Open / In Progress / Closed / Deferred
| Opened_Date | Date raised
| Closed_Date | Date closed (blank if open)
| MTTR_Days | Formula: Closed_Date − Opened_Date
Sprint_Overview | Sprint_ID | Sprint number
| Phase | High‑level engineering phase/focus
| Goal / Focus | Narrative goal statement for the sprint

## Dashboard
Dashboard
Charts & KPIs auto‑populate

## OKR_Epic_Map
Objective | Key Result | Epic Name | Epic Owner | Target Release | Status (%) | Comments
reading the Vehicle parameters | Circuit design to read the vehicle parameter | Circuit Integration | Kamesh , Rahul | v1.0 | 100 | all sensors & system functionality
Monitor for Excessive Vibration | Buzzer activates when vibration count reaches 5 or 10 | Vibration Monitoring Module | Jayanth | v1.1 | 100 | Stable vibration counter implemented with buzzer trigger logic
Track Ambient Conditions | DHT11 → Motor ON if Temp >24°C OR Humidity >80% | Environmental Sensing Integration | Aiswarya, Karishma | v1.2 | 100 | Tested with varying conditions; motor starts reliably
Provide Proximity Warning | IR sensor triggers buzzer on obstacle detection | Obstacle Detection & Safety Alert | Jayanth | v1.3 | 100 | Buzzer activates instantly upon obstacle detection
Display Real-Time Fuel Status | Water level sensor maps % to LED bar graph | Fuel Monitoring & Display Module | Aiswarya, Karishma | v1.4 | 100 | LED bar graph shows fuel level in real time
Validate System Stability | Integrated relay, motor, buzzer function without failure under load | Relay & Peripheral Integration | Kamesh , Rahul | v1.5 | 100 | Relay tested with motor & buzzer, no glitches
Execute Final System Integration | Debugging, integration & validation of all modules | Final Testing & Validation | Jayanth | v1.6 | 100 | All modules integrated & validated
Prepare Presentation | Documentation & final presentation prepared | Documentation & Presentation | Sreenivas | v1.7 | 100 | Final PPT & Report submitted

## Sprint_Overview
| S No | Epic | Purpose / Notes
| 1 | Architecture, Design & H/W Setup | - Perform architecture spike and feasibility studies (time-boxed) - Finalize design specifications and component selection - Assemble hardware boards- Install toolchains, flash utilities, and verify basic setup via “Hello World” style firmware - Collaborate on interface definition and pin mappings
| 2 | Coding & Unit Testing | - Implement features incrementally following stories - Practice Test Driven Development (TDD) - Perform code reviews and follow CI practices- Conduct unit-level smoke tests and ensure commit stability - Create reusable modules and maintain clean architecture
| 3 | Integration, FuncTesting, Git Mgmnt & ScrumMaster | - Integrate subsystems and verify end-to-end functionality - Write functional test cases and define acceptance criteria - Manage branches, merges, and pull requests - ScrumMaster facilitates daily standups, backlog grooming, sprint planning, reviews and retrospectives - Ensure traceability from user stories to code & test artifacts
| 4 | Debugging & Bug Fixing | - Analyze failures, logs, and use tools like oscilloscopes or logic analyzers - Conduct defect triaging and prioritization - Resolve root causes and perform bug-fix sprints- Refactor for code maintainability and readability - Validate fixes with regression testing
| 5 | Documentation & Presentation | - Prepare user manuals and internal technical documentation - Update versioned knowledge-base (e.g., Confluence, Notion) - Create demo boards/slides for sprint review or final showcase - Capture learnings, issues faced, and proposed improvements - Conduct hand-offs or stakeholder walkthroughs
Project Example
Sprint_ID | Week | Epic | Focus
1 | 1 | Architecture, Design & H/W Setup | • Design system architecture for vehicle health monitoring system (modular, reliable). • Set up STM32F405RGT6 and connect RFID, vibration sensor, DHT11, IR sensor, water level sensor, LED bar graph, relay, motor, and buzzer. • Verify power supply, pin mapping, and initial sensor communication.
|  | Coding & Unit Testing | • Develop test code to verify each peripheral: – RFID unlock sequence – Vibration counter (trigger buzzer at counts 5 & 10) – DHT11 (motor ON if Temp >24°C or Humidity >80%) – IR sensor (buzzer ON when obstacle detected) – Water level sensor with LED bar graph fuel display • Validate relay, motor, and buzzer functionality.
2 | 2 | Integration, Functional Testing, Git Mgmt & Scrum | • Integrate all modules into a single system. • Validate system behavior: – RFID unlock required before sensors work – Buzzer logic correctly linked to vibration & IR sensors – Motor controlled via DHT11 outputs – Fuel percentage displayed on LED bar graph • Implement Git-based collaboration (branching, merging).
3 | 3 | Debugging & Bug Fixing | • Identify and fix integration issues: – Incorrect fuel % display – Missed vibration counts – False buzzer triggers from IR sensor – Temperature/humidity read errors • Refactor code for modularity, scalability, and efficient peripheral usage.
|  | Documentation & Presentation | • Prepare detailed user & developer documentation. • Create system block diagram and flowchart. • Record demo of vehicle health monitoring system functionality. • Deliver structured PPT & final project presentation.

## Sprint_Backlog
Sprint_ID | Story_ID | Story_Title | Task Description | Epic | Story_Points | Owner | Status | Start_Date | End_Date | Days_Remaining | Percent_Complete
1 | 1 | Circuit Initialization | Initialize the Circuit, and verify system unlock functionality. | Circuit Security Integration | 3 | Aiswarya,Karishma | Done | 18.09.2025 | 23.09.2025 | 0 | 100%
1 | 2 | Vibration Setup | Configure GPIO and counter logic to manage input from the vibration sensor. | Vibration Monitoring | 3 | Kamesh ,Rahul | Done | 18.09.2025 | 23.09.2025 | 0 | 100%
1 | 3 | DHT11 Initialization | Implement the single-wire protocol for the DHT11 sensor to read temperature and humidity. | Environmental Monitoring | 3 | Jayanth | Done | 18.09.2025 | 23.09.2025 | 0 | 100%
1 | 4 | IR Sensor Setup | Set up a GPIO interrupt for obstacle detection and link the trigger directly to the buzzer. | Obstacle Detection | 2 | Jayanth | Done | 18.09.2025 | 23.09.2025 | 0 | 100%
1 | 5 | Fuel Level Display | Configure ADC for the water level sensor and map the percentage to the LED bar graph display. | Fuel Monitoring & Display | 3 | Aiswarya,Karishma | Done | 19.09.2025 | 25.09.2025 | 0 | 100%
2 | 1 | Vibration Alert Logic | Implement logic to trigger the buzzer when the vibration count reaches the threshold | Vibration Monitoring | 3 | Kamesh ,Rahul | Done | 19.09.2025 | 25.09.2025 | 0 | 100%
2 | 2 | Environmental Motor Control | Activate motor if the environment conditions meet the threshold criteria | Environmental Monitoring | 3 | Jayanth | Done | 19.09.2025 | 25.09.2025 | 0 | 100%
2 | 3 | Obstacle Alert Logic | Enable the buzzer instantly upon an obstacle detection event. | Obstacle Detection | 2 | Jayanth | Done | 19.09.2025 | 25.09.2025 | 0 | 100%
2 | 4 | Motor Integration Test | Integrate the relay to control the motor and test stability under load. | Relay & Peripheral Integration | 2 | Aiswarya,Karishma | Done | 19.09.2025 | 25.09.2025 | 0 | 100%
2 | 5 | Serial Data Output | Print all sensor values for serial debugging. | Debugging & Monitoring | 2 | Jayanth | Done | 19.09.2025 | 25.09.2025 | 0 | 100%
3 | 1 | Code Refactoring | Remove redundant code, improve modularity, and enhance power efficiency. | Final Debugging & Fixing | 3 | Kamesh ,Rahul | Done | 26.09.2025 | 29.09.2025 | 0 | 100%
3 | 2 | Sensor Error Recovery | Add recovery logic for handling missed or invalid readings from the DHT11, and vibration sensors. | Final Debugging & Fixing | 3 | Jayanth | Done | 26.09.2025 | 29.09.2025 | 0 | 100%
3 | 3 | Display Calibration | Adjust thresholds on the LED bar graph to ensure accurate fuel level representation. | Fuel Monitoring & Display | 2 | Aiswarya,Karishma | Done | 26.09.2025 | 29.09.2025 | 0 | 100%
3 | 4 | Noise Debugging | Fix false buzzer triggers that result from IR or vibration sensor noise. | Bug Fix | 2 | Jayanth | Done | 26.09.2025 | 29.09.2025 | 0 | 100%
3 | 5 | Report Preparation | Prepare the system block diagram, flowchart, and the final report. | Documentation | 3 | M.Sreenivas | Done | 29.09.2025 | 30.09.2025 | 0 | 100%
3 | 6 | System Demo Recording | Record a full system demonstration video | Documentation & Presentation | 3 | M.Sreenivas | Done | 29.09.2025 | 30.09.2025 | 0 | 100%
3 | 7 | Presentation Creation | Create and present the final PPT | Presentation | 3 | M.Sreenivas | Done | 29.09.2025 | 30.09.2025 | 0 | 100%
3 | 8 | Narrated Video Record | Record a narrated video version of the final presentation. | Presentation | 3 | M.Sreenivas | Done | 29.09.2025 | 30.09.2025 | 0 | 100%

## Velocity_Data
Sprint_ID | Story_Points_Committed | Story_Points_Completed
1 | 14 | 14
2 | 12 | 12
3 | 22 | 22

## Defect_Log
Defect_ID | Summary | Defect ID | Severity (1‑5) | Sprint_Found | Sprint_Fixed | Status | Opened_Date | Closed_Date | MTTR_Days

## Burndown_Template
Day | Planned_Remaining | Actual_Remaining
1 | 54 | 54
2 | 50 | 52
3 | 46 | 48
4 | 41 | 43
5 | 36 | 38
6 | 31 | 34
7 | 27 | 30
8 | 23 | 25
9 | 20 | 22
10 | 15 | 18
11 | 11 | 14
12 | 8 | 10
13 | 5 | 7
14 | 4 | 6
15 | 1 | 2

## Defect_Trend
Sprint_ID | New_Defects | Closed_Defects
1 | 4 | 3
2 | 6 | 5
3 | 7 | 6