## in
Task ID | Project Name | Team | Phase | Owner(s) | Start Date | End Date | Completion (%) | Status | Task Description | Comments | Story
Task 0 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Requirement Gathering | Aiswarya P, Jayanth Kolisetty | 2025-06-25 | 2025-06-26 | 100 | Completed | Identified project needs and defined goals with team and mentor. | Clear understanding of objectives. | We kicked off by defining objectives and deliverables with the mentor.
Task 1 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Stakeholder Interviews | Rahul Sharma | 2025-06-27 | 2025-06-30 | 100 | Completed | Interviewed stakeholders to understand on-ground challenges. | Captured real-world feedback from stakeholders. | Team interviewed factory staff to uncover real challenges.
Task 2 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Literature Review | Aiswarya P | 2025-07-01 | 2025-07-02 | 100 | Completed | Reviewed research papers and industry guidelines to set direction. | Aligned thresholds with Kavin et al. 2019. | Reviewed papers like Kavin et al. 2019 and OSHA guidelines for benchmarks.
Task 3 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Threshold Definition | Rahul Sharma | 2025-07-03 | 2025-07-04 | 100 | Completed | Defined safety thresholds based on literature and OSHA standards. | Benchmarked to literature values. | Defined target thresholds of 27°C and 73% RH for safety.
Task 4 | Textile Industry Safety Monitoring Project | SILICON SQUAD | System Architecture Design | Rahul Sharma | 2025-07-07 | 2025-07-08 | 100 | Completed | Designed high-level architecture of the system. | Reviewed and approved by mentor. | Drafted system architecture showing data flow from sensors to actuators.
Task 5 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Circuit Schematic Design | Aiswarya P, Jayanth Kolisetty | 2025-07-09 | 2025-07-10 | 100 | Completed | Created detailed circuit schematic of sensors, MCU and actuators. | Accurate and neat schematic drawn. | Detailed circuit diagram created for clarity and implementation.
Task 6 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Component Selection | Jayanth Kolisetty | 2025-07-11 | 2025-07-14 | 100 | Completed | Selected components and ordered hardware parts. | Sourcing completed within budget. | Procured all required components after market research.
Task 7 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Pin Mapping | Rahul Sharma | 2025-07-11 | 2025-07-14 | 100 | Completed | Mapped STM32 pins to components ensuring no conflicts. | No conflicts found in pin assignments. | Mapped STM32 pins ensuring all connections were logical.
Task 8 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Breadboard Assembly | Aiswarya P, Jayanth Kolisetty | 2025-07-11 | 2025-07-14 | 100 | Completed | Assembled components on breadboard with proper layout. | Assembly was clean and stable. | Hardware assembled cleanly on breadboard with labels.
Task 9 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Power Rail Setup | Jayanth Kolisetty | 2025-07-11 | 2025-07-14 | 100 | Completed | Set up stable power rails for 3.3V and 5V requirements. | Power was steady, no shorts. | Ensured power delivery was stable and safe for components.
Task 10 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Sensor Testing | Karishma | 2025-07-11 | 2025-07-14 | 100 | Completed | Tested each sensor individually for proper readings. | All sensors calibrated successfully. | Calibrated sensors to ensure accuracy before integration.
Task 11 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Actuator Testing | Sri Kamesh Guru | 2025-07-11 | 2025-07-14 | 100 | Completed | Verified actuators (motor, buzzer, LEDs) worked as expected. | Actuators responsive and reliable. | Checked all output devices functioned properly when triggered.
Task 12 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Embedded Software Development | Karishma, Sri Kamesh Guru | 2025-07-11 | 2025-07-14 | 100 | Completed | Wrote embedded C code to interface sensors and actuators. | Code compiled and loaded successfully. | Developed firmware to read inputs and control outputs.
Task 13 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Debugging & Optimization | Rahul Sharma | 2025-07-11 | 2025-07-14 | 100 | Completed | Debugged software, optimized for better response time. | Removed minor bugs and improved loop timings. | Debugged issues and improved code efficiency.
Task 14 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Integration Testing | Rahul Sharma | 2025-07-11 | 2025-07-14 | 100 | Completed | Integrated hardware and software into functioning prototype. | Integration successful with minor interference. | Integrated hardware & software to create working prototype.
Task 15 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Threshold Validation | Aiswarya P, Karishma | 2025-07-11 | 2025-07-14 | 100 | Completed | Validated system at thresholds of 27°C and 73% RH. | System behaved correctly at thresholds. | Tested system against defined thresholds successfully.
Task 16 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Final Testing & QA | Full Team | 2025-07-11 | 2025-07-14 | 100 | Completed | Performed final system testing and quality assurance. | Final checks done, system reliable. | Performed complete QA to confirm performance.
Task 17 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Documentation Writing | Aiswarya P | 2025-07-11 | 2025-07-14 | 100 | Completed | Documented all phases, results, and lessons learned. | Draft completed, awaiting feedback. | Compiled project documentation with all findings.
Task 18 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Presentation Preparation | Rahul Sharma | 2025-07-11 | 2025-07-14 | 100 | Completed | Prepared final presentation slides and visuals. | Slides visually appealing and concise. | Designed presentation to clearly convey the project.
Task 19 | Textile Industry Safety Monitoring Project | SILICON SQUAD | Team Review | Full Team | 2025-07-11 | 2025-07-14 | 100 | Completed | Conducted internal team review and rehearsal before demo. | Team aligned and ready for final presentation. | Rehearsed the presentation as a team and made final adjustments.