## Project_1
Project Start Date | 25-6-2025 | Project | Real Time Industrial Safety System
Pune - Project-1 Status as on 15th July 2025
Team | Associates | Roles | Task | Status
Silicon Squad | Sri Kamesh Guru R | Architecture, Hardware Setup, Design | Design and assemble the circuit based on component specifications and STM32 connections. | Completed
|  |  | Solder and connect components including sensors, motor driver, and STM32F405 on a breadboard or PCB. | Completed
|  |  | Ensure proper power distribution from external 5V supply and STM32 3.3V. | Completed
|  |  | Validate sensor connections and signal integrity using a multimeter/oscilloscope. | Completed
|  |  | Integrate all hardware modules into a single physical prototype for testing. | Completed
| Aiswarya P | Software Design, Coding & Unit Testing, Debugging and Bug Fixing | Software Architecture and Discussed about Sensor | Completed
|  |  | Algorithm and flow chart for DHT11 | Completed
|  |  | Algorithm and flow chart for PIR sensor | Completed
|  |  | Interface DHT11 with STM32 | Completed
|  |  | Interfacing All the components | Completed
|  |  | Motor Control Code Development | Completed
| Karishma BB | ARCHITECT,DESIGN,H/W SETUP | Define system block diagram and data flow between components. | Completed
|  |  | Choose appropriate microcontroller pins based on function and constraints. | Completed
|  |  | Create the schematic diagram showing all sensor and motor driver wiring. | Completed
|  |  | Validate power requirements for all components and plan the supply. | Completed
|  |  | Guide design of modular software and hardware structure. | Completed
| Rahul Kumar Sharma | Integration, Functional Testing | Combine hardware and software modules for full system operation. | Completed
|  |  | Test the system in scenarios with actual temperature, motion, and vibration events. | Completed
|  |  | Verify buzzer, LED, and motor responses to various sensor combinations. | Completed
|  |  | Record observations during testing and compare with expected outputs. | Completed
|  |  | Identify integration issues such as missed sensor inputs or timing delays. | Completed
|  |  | Communicate bugs or inconsistencies to coding and hardware teams. | Completed
| Kolisetty Jayanth | Scrum Master, Documentation | Schedule regular scrum meetings and track progress of each member. | Completed
|  |  | Maintain the sprint board and task completion status. | Completed
|  |  | Document all pin mappings and component connections with references. | Completed
|  |  | Create the flowchart, block diagram, and schematic for final report. | Completed
Team 2 | Prasanthi | Integration,Function TEST,GIT HUB Management | Role distribution,Task allocation | Completed
|  |  | Schematic development of motor drive & dc motor | Completed
|  |  | Building the test case for PIR Sensor | Completed
|  |  | Building the test case for tempreture | Completed
|  |  | Documentation | Completed
| Rambarath | CODE,DEBUG,Testing | Software Architecture and Discussed about Sensor | Completed
|  |  | Algorithm and flow chart for DHT11 | Completed
|  |  | Algorithm and flow chart for PIR sensor | Completed
|  |  | Interface DHT11 with STM32 | Completed
|  |  | Interfacing All the components | Completed
|  |  | Motor Control Code Development | Completed
| Kiruthigha | ARCHITECT,DESIGN,H/W SETUP | Hardware Architecture and overview of the Hardware | Completed
|  |  | Circuit Diagram and flow chart for DHT11 | Completed
|  |  | Algorithm and flow chart for Relay | Completed
|  |  | GITHUB MANAGEMENT | Completed
|  |  | Review,Reading Datasheet for pin confg and schematic of Relay | Completed
| Kalpana | ARCHITECT,DESIGN,H/W SETUP | Discussion & review of the hardware requirement | Completed
|  |  | Analysis and implementation of pin configuration of project | Completed
|  |  | Schematic Development for Circuit Diagram | Completed
|  |  | Analysis and schematic development of Vibration Sensor | Completed
|  |  | Vibration sensor Circuit Connection | Completed
|  |  | Relay Circuit Connection | Completed
| Sivanesh | Unit Testing and Functional Testing | Study of Hardware | Completed
|  |  | Unit Testing using CPP test | Completed
|  |  | Debugging and Bug Fixing | Completed
|  |  | Software Architecture and Discussed about Vibration Sensor | Completed
TEAM 3 | Anis Chelse N | Debugging , Integration,Function Testing, Documentation | Requirement Study and Prepare Story and TASK | Completed
|  |  | Ultrasonic Sensor functional Requirements | Completed
|  |  | Thermistor Interface functional Requirements | Completed
|  |  | DC Motor functional Requirements | Completed
|  |  | Relay functional Requirements | Completed
|  |  | Vibration sensor functional requirements | Completed
|  |  | Integration of thermistor with DC motor and Relay | Completed
|  |  | Integration of Vibration sensor with DC motor and Driver | Completed
|  |  | Functional Test of Ultrasonic Sensor | Completed
|  |  | Functional Test of thermistor | Completed
|  |  | Functional Test of Buzzer | Completed
|  |  | Functional Test of Motor Driver | Completed
| Arun M | Architecture, Hardware setup, Design, Presentation | Requirement Study and Prepare Story and TASK | Completed
|  |  | Schematic Development for Thermistor | Completed
|  |  | Schematic Development for Ultrasonic Sensor | Completed
|  |  | Schematic Development for Vibration sensor | Completed
|  |  | Complete Schematic Development | Completed
|  |  | Hardware connection of Ultrasonic sensor | Completed
|  |  | Hardware Connection of thermistor | Completed
|  |  | Hardware connection of Vibration sensor | Completed
|  |  | Hardware connection of DC motor and Driver | Completed
|  |  | Final presentation with Scenarios and Screenshots | Completed
|  |  | Overall Progress Tracker | Completed
|  |  | Functional Test of Photoresistor | Completed
|  |  | Functional Test of LED Flashed | Completed
|  |  | Integration of DHT11 sensor Temperature code with DC Motor as per the algorithm | Completed
|  |  | Integration of DHT11 Sensor Humidity reading with Relay and Bulb as per the algorithm | Completed
|  |  | Functional Test of Motor | Completed
|  |  | Functional Test of Relay Working | Completed
| Deivanayaki B | Debugging , Integration,Function Testing, Documentation | Requirement Study and Prepare Story and TASK for ASSOCIATE 5 | Completed
|  |  | thermistor Hardware requirements | Completed
|  |  | Ultrasonic Sensor HardwareRequirements | Completed
|  |  | Vibration sensor hardware requirements | Completed
|  |  | Relay and DC motor Hardware requirements | Completed
|  |  | Requirement specifiction documentation | Completed
|  |  | Integration of Ultrasonic sensor with On Board Buzzer | Completed
|  |  | Integration of Complete Module | Completed
|  |  | Functional Test of Vibration Sensor | Completed
|  |  | Functional Test of Motor | Completed
|  |  | Functional Test of Relay Working | Completed
| Dharsika S | Coding, Interfacing & Unit Testing , GIT Management | Requirement Study and S/W architecture | Completed
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 2 | Completed
|  |  | Installing GIT | Completed
|  |  | Creating a remote repository | Completed
|  |  | Making the initial push to the repository | Completed
|  |  | Schematic Development for Relay Module | Completed
|  |  | Ultrasonic Sensor Flow chart | Completed
|  |  | Thermistor and Vibration sensor Flowchart | Completed
|  |  | Overall Flowchart | Completed
|  |  | Unit test of Vibration Sensor | Completed
|  |  | Unit test of DC Motor wih Driver | Completed
|  |  | Unit test of Relay | Completed
|  |  | Debugging the Ultrasonic Timer Module | Completed
|  |  | Debugging the delay of FreeRTOS tasks | Completed
|  |  | Final GIT Push | Completed
|  |  | Schmetic of LDR and LED BAR GRAPH | Completed
| Surendhar A | Coding , Interfacing & Unit Testing, Scrum Master | Requirement Study and Prepare Story and TASK | Completed
|  |  | Task assigning, Helping in H/W Setup | Completed
|  |  | Familirizing the GIT commands | Completed
|  |  | Creating ssh tokens in GITHUB | Completed
|  |  | Schematic Development for DC motor with driver | Completed
|  |  | Code Development for thermistor | Completed
|  |  | DC motor code development | Completed
|  |  | Code Development for Vibration sensor | Completed
|  |  | DC motor driver code development | Completed
|  |  | Code Development for Ultrasonic sensor | Completed
|  |  | Relay code Development | Completed
|  |  | Integrating FreeRTOS and Interrupts | Completed
|  |  | Unit test of thermistor | Completed
|  |  | Unit test of Ultrasonic Sensor | Completed
|  |  | Unit test of ADC Units in uC | Completed
|  |  | Debugging the Thermistor ADC module | Completed
|  |  | Debugging the Sensitivity of Vibration sensor module | Completed
|  |  | Debugging the Duty Cycle to the PWM module for Motor Driver | Completed
|  |  | Debugging the ISR Issues | Completed
Team 4 | Dev Anchal | Coding & Unit Testing, Debugging and Bug Fixing | Implement sensor driver code for DHT11, PIR, and vibration sensor in C/C++ using STM32 HAL. | Completed
|  |  | Write control logic for DC motor and buzzer activation based on sensor inputs. | Completed
|  |  | Develop modular code functions to ensure testability and reuse. | Completed
|  |  | Write unit tests using CppUTest for motor control and alert logic. | Completed
|  |  | Debug initialization and communication issues on STM32 pins. | Completed
|  |  | Fix bugs related to timing, sensor readings, or PWM signal behavior. | Completed
|  |  | Simulate edge cases like over-temperature or vibration to validate code. | Completed
|  |  | Refactor code based on feedback from integration and testing team. | Completed
|  |  | Maintain version control and commit tested modules to the repository. | Completed
|  |  | Provide weekly code status updates during scrum meetings. | Completed
| Surya Prakash Singh | Scrum Master, Documentation | Requirement Study and Prepare Story and TASK for ASSOCIATE 4 | Completed
|  |  | Algorithm and Flow Chart Development for DC Motor | Completed
|  |  | Flow Chart of LDR and Helping in H/W | Completed
|  |  | Schematic Development for DC Motor and Motor Driver with STM uC | Completed
|  |  | DHT11 Sensor Intreface and functional Requirements | Completed
| Ruban Mariappan | Hardware setup, Design, Integration | DHT11 Sensor Interface with uC | In Progress
|  |  | DHT11 Circuit Connection, Flow Chart | Completed
|  |  | Photoresistor Circuit Connection and helping in hardware setup | Completed
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 0 | Completed
|  |  | Task assign., Helping in H/W Setup | Completed
|  |  | Photoresistor Interface with uC and connection of led bar. | Completed
|  |  | Photoresistor Interface and code development | Completed
|  |  | KeyPad Circuit Connection and managing tracker, Studying about the components. | Completed
| Vishawjeet Singh | Architecture, Hardware Setup, Design | LED Flasher Circuit Connection, Working of Led Flasher | Completed
|  |  | Functional Test of Photoresistor | Completed
|  |  | Integration of Photoresistor Sensor code with LED Flasher as per the algorithm | Completed
|  |  | Daily Scrum | In Progress
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 3 | Completed
|  |  | Schematic Development for DHT11 Sensor with STM uC | Completed
|  |  | Schematic Development for Photoresistor with STM uC | Completed
|  |  | Complete Schematic Development | Completed
|  |  | Photoresistor Interface and functional Requirements | Completed

## Project_2
Project Start Date | 16-7-2025 | Project | Autonomous Green House Control System
Pune - Project-2 Status as on 5th August 2025
Team | Associates | Roles | Task | Status
Silicon Squad | Aishwarya P | Architecture, Hardware Setup, Design | Design and assemble the circuit based on component specifications and STM32 connections. | Completed
|  |  | Solder and connect components including sensors, motor driver, and STM32F405 on a breadboard or PCB. | Completed
|  |  | Ensure proper power distribution from external 5V supply and STM32 3.3V. | Completed
|  |  | Validate sensor connections and signal integrity using a multimeter/oscilloscope. | Completed
|  |  | Integrate all hardware modules into a single physical prototype for testing. | Completed
| Sri Kamesh Guru R | Software Design, Coding & Unit Testing, Debugging and Bug Fixing | Software Architecture and Discussed about Sensor | Completed
|  |  | Algorithm and flow chart for DHT11 | Completed
|  |  | Algorithm and flow chart for PIR sensor | Completed
|  |  | Interface DHT11 with STM32 | Completed
|  |  | Interfacing All the components | Completed
|  |  | Motor Control Code Development | Completed
| Rahul Kumar Sharma | ARCHITECT,DESIGN,H/W SETUP | Define system block diagram and data flow between components. | Completed
|  |  | Choose appropriate microcontroller pins based on function and constraints. | Completed
|  |  | Create the schematic diagram showing all sensor and motor driver wiring. | Completed
|  |  | Validate power requirements for all components and plan the supply. | Completed
|  |  | Guide design of modular software and hardware structure. | Completed
| Jayanth | Integration, Functional Testing | Combine hardware and software modules for full system operation. | Completed
|  |  | Test the system in scenarios with actual temperature, motion, and vibration events. | Completed
|  |  | Verify buzzer, LED, and motor responses to various sensor combinations. | Completed
|  |  | Record observations during testing and compare with expected outputs. | Completed
|  |  | Identify integration issues such as missed sensor inputs or timing delays. | Completed
|  |  | Communicate bugs or inconsistencies to coding and hardware teams. | Completed
| Karishma BB | Scrum Master, Documentation | Schedule regular scrum meetings and track progress of each member. | Completed
|  |  | Maintain the sprint board and task completion status. | Completed
|  |  | Document all pin mappings and component connections with references. | Completed
|  |  | Create the flowchart, block diagram, and schematic for final report. | Completed
Team 2 | Rambarath | Integration,Function TEST,GIT HUB Management | Role distribution,Task allocation | Completed
|  |  | Schematic development of motor drive & dc motor | Completed
|  |  | Building the test case for PIR Sensor | Completed
|  |  | Building the test case for tempreture | Completed
|  |  | Documentation | Completed
| Kiruthigha | CODE,DEBUG,Testing | Software Architecture and Discussed about Sensor | Completed
|  |  | Algorithm and flow chart for DHT11 | Completed
|  |  | Algorithm and flow chart for PIR sensor | Completed
|  |  | Interface DHT11 with STM32 | Completed
|  |  | Interfacing All the components | Completed
|  |  | Motor Control Code Development | Completed
| Prasanthi | ARCHITECT,DESIGN,H/W SETUP | Hardware Architecture and overview of the Hardware | Completed
|  |  | Circuit Diagram and flow chart for DHT11 | Completed
|  |  | Algorithm and flow chart for Relay | Completed
|  |  | GITHUB MANAGEMENT | Completed
|  |  | Review,Reading Datasheet for pin confg and schematic of Relay | Completed
| Sivanesh | ARCHITECT,DESIGN,H/W SETUP | Discussion & review of the hardware requirement | Completed
|  |  | Analysis and implementation of pin configuration of project | Completed
|  |  | Schematic Development for Circuit Diagram | Completed
|  |  | Analysis and schematic development of Vibration Sensor | Completed
|  |  | Vibration sensor Circuit Connection | Completed
|  |  | Relay Circuit Connection | Completed
| Kalpana | Unit Testing and Functional Testing | Study of Hardware | Completed
|  |  | Unit Testing using CPP test | Completed
|  |  | Debugging and Bug Fixing | Completed
|  |  | Software Architecture and Discussed about Vibration Sensor | Completed
TEAM 3 | Surendhar A | Debugging , Integration,Function Testing, Documentation | Requirement Study and Prepare Story and TASK | Completed
|  |  | Ultrasonic Sensor functional Requirements | Completed
|  |  | Thermistor Interface functional Requirements | Completed
|  |  | DC Motor functional Requirements | Completed
|  |  | Relay functional Requirements | Completed
|  |  | Vibration sensor functional requirements | Completed
|  |  | Integration of thermistor with DC motor and Relay | Completed
|  |  | Integration of Vibration sensor with DC motor and Driver | Completed
|  |  | Functional Test of Ultrasonic Sensor | Completed
|  |  | Functional Test of thermistor | Completed
|  |  | Functional Test of Buzzer | Completed
|  |  | Functional Test of Motor Driver | Completed
| Deivanayaki B | Architecture, Hardware setup, Design, Git Management | Requirement Study and Prepare Story and TASK | Completed
|  |  | Schematic Development for Thermistor | Completed
|  |  | Schematic Development for Ultrasonic Sensor | Completed
|  |  | Schematic Development for Vibration sensor | Completed
|  |  | Complete Schematic Development | Completed
|  |  | Hardware connection of Ultrasonic sensor | Completed
|  |  | Hardware Connection of thermistor | Completed
|  |  | Hardware connection of Vibration sensor | Completed
|  |  | Hardware connection of DC motor and Driver | Completed
|  |  | Final presentation with Scenarios and Screenshots | Completed
|  |  | Overall Progress Tracker | Completed
|  |  | Functional Test of Photoresistor | Completed
|  |  | Functional Test of LED Flashed | Completed
|  |  | Integration of DHT11 sensor Temperature code with DC Motor as per the algorithm | Completed
|  |  | Integration of DHT11 Sensor Humidity reading with Relay and Bulb as per the algorithm | Completed
|  |  | Functional Test of Motor | Completed
|  |  | Functional Test of Relay Working | Completed
| Dharsika S | Integration,Function Testing, Scrum Master | Requirement Study and Prepare Story and TASK for ASSOCIATE 5 | Completed
|  |  | thermistor Hardware requirements | Completed
|  |  | Ultrasonic Sensor HardwareRequirements | Completed
|  |  | Vibration sensor hardware requirements | Completed
|  |  | Relay and DC motor Hardware requirements | Completed
|  |  | Requirement specifiction documentation | Completed
|  |  | Integration of Ultrasonic sensor with On Board Buzzer | Completed
|  |  | Integration of Complete Module | Completed
|  |  | Functional Test of Vibration Sensor | Completed
|  |  | Functional Test of Motor | Completed
|  |  | Functional Test of Relay Working | Completed
| Anis Chelse N | Coding, Interfacing & Unit Testing | Requirement Study and S/W architecture | Completed
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 2 | Completed
|  |  | Installing GIT | Completed
|  |  | Creating a remote repository | Completed
|  |  | Making the initial push to the repository | Completed
|  |  | Schematic Development for Relay Module | Completed
|  |  | Ultrasonic Sensor Flow chart | Completed
|  |  | Thermistor and Vibration sensor Flowchart | Completed
|  |  | Overall Flowchart | Completed
|  |  | Unit test of Vibration Sensor | Completed
|  |  | Unit test of DC Motor wih Driver | Completed
|  |  | Unit test of Relay | Completed
|  |  | Debugging the Ultrasonic Timer Module | Completed
|  |  | Debugging the delay of FreeRTOS tasks | Completed
|  |  | Final GIT Push | Completed
|  |  | Schmetic of LDR and LED BAR GRAPH | Completed
| Arun M | Coding , Interfacing & Presentation | Requirement Study and Prepare Story and TASK | Completed
|  |  | Task assigning, Helping in H/W Setup | Completed
|  |  | Familirizing the GIT commands | Completed
|  |  | Creating ssh tokens in GITHUB | Completed
|  |  | Schematic Development for DC motor with driver | Completed
|  |  | Code Development for thermistor | Completed
|  |  | DC motor code development | Completed
|  |  | Code Development for Vibration sensor | Completed
|  |  | DC motor driver code development | Completed
|  |  | Code Development for Ultrasonic sensor | Completed
|  |  | Relay code Development | Completed
|  |  | Integrating FreeRTOS and Interrupts | Completed
|  |  | Unit test of thermistor | Completed
|  |  | Unit test of Ultrasonic Sensor | Completed
|  |  | Unit test of ADC Units in uC | Completed
|  |  | Debugging the Thermistor ADC module | Completed
|  |  | Debugging the Sensitivity of Vibration sensor module | Completed
|  |  | Debugging the Duty Cycle to the PWM module for Motor Driver | Completed
|  |  | Debugging the ISR Issues | Completed
Team 4 | Ruban Mariappan | Coding & Unit Testing, Debugging and Bug Fixing | Implement sensor driver code for DHT11, PIR, and vibration sensor in C/C++ using STM32 HAL. | Completed
|  |  | Write control logic for DC motor and buzzer activation based on sensor inputs. | Completed
|  |  | Develop modular code functions to ensure testability and reuse. | Completed
|  |  | Write unit tests using CppUTest for motor control and alert logic. | Completed
|  |  | Debug initialization and communication issues on STM32 pins. | Completed
|  |  | Fix bugs related to timing, sensor readings, or PWM signal behavior. | Completed
|  |  | Simulate edge cases like over-temperature or vibration to validate code. | Completed
|  |  | Refactor code based on feedback from integration and testing team. | Completed
|  |  | Maintain version control and commit tested modules to the repository. | Completed
|  |  | Provide weekly code status updates during scrum meetings. | Completed
| Dev Anchal | Scrum Master, Documentation | Requirement Study and Prepare Story and TASK for ASSOCIATE 4 | Completed
|  |  | Algorithm and Flow Chart Development for DC Motor | Completed
|  |  | Flow Chart of LDR and Helping in H/W | Completed
|  |  | Schematic Development for DC Motor and Motor Driver with STM uC | Completed
|  |  | DHT11 Sensor Intreface and functional Requirements | Completed
| Surya Prakash Singh | Hardware setup, Design, Integration | DHT11 Sensor Interface with uC | Completed
|  |  | DHT11 Circuit Connection, Flow Chart | Completed
|  |  | Photoresistor Circuit Connection and helping in hardware setup | Completed
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 0 | Completed
|  |  | Task assign., Helping in H/W Setup | Completed
|  |  | Photoresistor Interface with uC and connection of led bar. | Completed
|  |  | Photoresistor Interface and code development | Completed
|  |  | KeyPad Circuit Connection and managing tracker, Studying about the components. | Completed
| Vishawjeet Singh | Architecture, Hardware Setup, Design | LED Flasher Circuit Connection, Working of Led Flasher | Completed
|  |  | Functional Test of Photoresistor | Completed
|  |  | Integration of Photoresistor Sensor code with LED Flasher as per the algorithm | Completed
|  |  | Daily Scrum | Completed
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 3 | Completed
|  |  | Schematic Development for DHT11 Sensor with STM uC | Completed
|  |  | Schematic Development for Photoresistor with STM uC | Completed
|  |  | Complete Schematic Development | Completed
|  |  | Photoresistor Interface and functional Requirements | Completed

## Project_3
Project Start Date | 2025-06-08 | Project | Smart Traffic Light Control System
Pune - Project-3 Status as on 28th August 2025
Team | Associates | Roles | Task | Status
Silicon Squad | Aishwarya P | Architecture, Hardware Setup, Design | Design and assemble the circuit based on component specifications and STM32 connections. | Completed
|  |  | Solder and connect components including sensors, motor driver, and STM32F405 on a breadboard or PCB. | Completed
|  |  | Ensure proper power distribution from external 5V supply and STM32 3.3V. | Completed
|  |  | Validate sensor connections and signal integrity using a multimeter/oscilloscope. | Completed
|  |  | Integrate all hardware modules into a single physical prototype for testing. | Completed
| Sri Kamesh Guru R | Software Design, Coding & Unit Testing, Debugging and Bug Fixing | Software Architecture and Discussed about Sensor | Completed
|  |  | Algorithm and flow chart for DHT11 | Completed
|  |  | Algorithm and flow chart for PIR sensor | Completed
|  |  | Interface DHT11 with STM32 | Completed
|  |  | Interfacing All the components | Completed
|  |  | Motor Control Code Development | Completed
| Rahul Kumar Sharma | ARCHITECT,DESIGN,H/W SETUP | Define system block diagram and data flow between components. | Completed
|  |  | Choose appropriate microcontroller pins based on function and constraints. | Completed
|  |  | Create the schematic diagram showing all sensor and motor driver wiring. | Completed
|  |  | Validate power requirements for all components and plan the supply. | Completed
|  |  | Guide design of modular software and hardware structure. | Completed
| Jayanth | Integration, Functional Testing | Combine hardware and software modules for full system operation. | Completed
|  |  | Test the system in scenarios with actual temperature, motion, and vibration events. | Completed
|  |  | Verify buzzer, LED, and motor responses to various sensor combinations. | Completed
|  |  | Record observations during testing and compare with expected outputs. | Completed
|  |  | Identify integration issues such as missed sensor inputs or timing delays. | Completed
|  |  | Communicate bugs or inconsistencies to coding and hardware teams. | Completed
| Karishma BB | Scrum Master, Documentation | Schedule regular scrum meetings and track progress of each member. | Completed
|  |  | Maintain the sprint board and task completion status. | Completed
|  |  | Document all pin mappings and component connections with references. | Completed
|  |  | Create the flowchart, block diagram, and schematic for final report. | Completed
Team 2 | Rambarath | Integration,Function TEST,GIT HUB Management | Role distribution,Task allocation | Completed
|  |  | Schematic development of motor drive & dc motor | Completed
|  |  | Building the test case for PIR Sensor | Completed
|  |  | Building the test case for tempreture | Completed
|  |  | Documentation | Completed
| Kiruthigha | CODE,DEBUG,Testing | Software Architecture and Discussed about Sensor | Completed
|  |  | Algorithm and flow chart for DHT11 | Completed
|  |  | Algorithm and flow chart for PIR sensor | Completed
|  |  | Interface DHT11 with STM32 | Completed
|  |  | Interfacing All the components | Completed
|  |  | Motor Control Code Development | Completed
| Prasanthi | ARCHITECT,DESIGN,H/W SETUP | Hardware Architecture and overview of the Hardware | Completed
|  |  | Circuit Diagram and flow chart for DHT11 | Completed
|  |  | Algorithm and flow chart for Relay | Completed
|  |  | GITHUB MANAGEMENT | Completed
|  |  | Review,Reading Datasheet for pin confg and schematic of Relay | Completed
| Kalpana | Unit Testing and Functional Testing | Study of Hardware | Completed
|  |  | Unit Testing using CPP test | Completed
|  |  | Debugging and Bug Fixing | Completed
|  |  | Software Architecture and Discussed about Vibration Sensor | Completed
TEAM 3 | Surendhar A | Debugging , Integration,Function Testing, Documentation | Requirement Study and Prepare Story and TASK | Completed
|  |  | Ultrasonic Sensor functional Requirements | Completed
|  |  | Thermistor Interface functional Requirements | Completed
|  |  | DC Motor functional Requirements | Completed
|  |  | Relay functional Requirements | Completed
|  |  | Vibration sensor functional requirements | Completed
|  |  | Integration of thermistor with DC motor and Relay | Completed
|  |  | Integration of Vibration sensor with DC motor and Driver | Completed
|  |  | Functional Test of Ultrasonic Sensor | Completed
|  |  | Functional Test of thermistor | Completed
|  |  | Functional Test of Buzzer | Completed
|  |  | Functional Test of Motor Driver | Completed
| Deivanayaki B | Architecture, Hardware setup, Design, Git Management | Requirement Study and Prepare Story and TASK | Completed
|  |  | Schematic Development for Thermistor | Completed
|  |  | Schematic Development for Ultrasonic Sensor | Completed
|  |  | Schematic Development for Vibration sensor | Completed
|  |  | Complete Schematic Development | Completed
|  |  | Hardware connection of Ultrasonic sensor | Completed
|  |  | Hardware Connection of thermistor | Completed
|  |  | Hardware connection of Vibration sensor | Completed
|  |  | Hardware connection of DC motor and Driver | Completed
|  |  | Final presentation with Scenarios and Screenshots | Completed
|  |  | Overall Progress Tracker | Completed
|  |  | Functional Test of Photoresistor | Completed
|  |  | Functional Test of LED Flashed | Completed
|  |  | Integration of DHT11 sensor Temperature code with DC Motor as per the algorithm | Completed
|  |  | Integration of DHT11 Sensor Humidity reading with Relay and Bulb as per the algorithm | Completed
|  |  | Functional Test of Motor | Completed
|  |  | Functional Test of Relay Working | Completed
| Dharsika S | Integration,Function Testing, Scrum Master | Requirement Study and Prepare Story and TASK for ASSOCIATE 5 | Completed
|  |  | thermistor Hardware requirements | Completed
|  |  | Ultrasonic Sensor HardwareRequirements | Completed
|  |  | Vibration sensor hardware requirements | Completed
|  |  | Relay and DC motor Hardware requirements | Completed
|  |  | Requirement specifiction documentation | Completed
|  |  | Integration of Ultrasonic sensor with On Board Buzzer | Completed
|  |  | Integration of Complete Module | Completed
|  |  | Functional Test of Vibration Sensor | Completed
|  |  | Functional Test of Motor | Completed
|  |  | Functional Test of Relay Working | Completed
| Anis Chelse N | Coding, Interfacing & Unit Testing | Requirement Study and S/W architecture | Completed
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 2 | Completed
|  |  | Installing GIT | Completed
|  |  | Creating a remote repository | Completed
|  |  | Making the initial push to the repository | Completed
|  |  | Schematic Development for Relay Module | Completed
|  |  | Ultrasonic Sensor Flow chart | Completed
|  |  | Thermistor and Vibration sensor Flowchart | Completed
|  |  | Overall Flowchart | Completed
|  |  | Unit test of Vibration Sensor | Completed
|  |  | Unit test of DC Motor wih Driver | Completed
|  |  | Unit test of Relay | Completed
|  |  | Debugging the Ultrasonic Timer Module | Completed
|  |  | Debugging the delay of FreeRTOS tasks | Completed
|  |  | Final GIT Push | Completed
|  |  | Schmetic of LDR and LED BAR GRAPH | Completed
| Arun M | Coding , Interfacing & Presentation | Requirement Study and Prepare Story and TASK | Completed
|  |  | Task assigning, Helping in H/W Setup | Completed
|  |  | Familirizing the GIT commands | Completed
|  |  | Creating ssh tokens in GITHUB | Completed
|  |  | Schematic Development for DC motor with driver | Completed
|  |  | Code Development for thermistor | Completed
|  |  | DC motor code development | Completed
|  |  | Code Development for Vibration sensor | Completed
|  |  | DC motor driver code development | Completed
|  |  | Code Development for Ultrasonic sensor | Completed
|  |  | Relay code Development | Completed
|  |  | Integrating FreeRTOS and Interrupts | Completed
|  |  | Unit test of thermistor | Completed
|  |  | Unit test of Ultrasonic Sensor | Completed
|  |  | Unit test of ADC Units in uC | Completed
|  |  | Debugging the Thermistor ADC module | Completed
|  |  | Debugging the Sensitivity of Vibration sensor module | Completed
|  |  | Debugging the Duty Cycle to the PWM module for Motor Driver | Completed
|  |  | Debugging the ISR Issues | Completed
Team 4 | Ruban Mariappan | Coding & Unit Testing, Debugging and Bug Fixing | Implement sensor driver code for DHT11, PIR, and vibration sensor in C/C++ using STM32 HAL. | Completed
|  |  | Write control logic for DC motor and buzzer activation based on sensor inputs. | Completed
|  |  | Develop modular code functions to ensure testability and reuse. | Completed
|  |  | Write unit tests using CppUTest for motor control and alert logic. | Completed
|  |  | Debug initialization and communication issues on STM32 pins. | Completed
|  |  | Fix bugs related to timing, sensor readings, or PWM signal behavior. | Completed
|  |  | Simulate edge cases like over-temperature or vibration to validate code. | Completed
|  |  | Refactor code based on feedback from integration and testing team. | Completed
|  |  | Maintain version control and commit tested modules to the repository. | Completed
|  |  | Provide weekly code status updates during scrum meetings. | Completed
| Dev Anchal | Scrum Master, Documentation | Requirement Study and Prepare Story and TASK for ASSOCIATE 4 | Completed
|  |  | Algorithm and Flow Chart Development for DC Motor | Completed
|  |  | Flow Chart of LDR and Helping in H/W | Completed
|  |  | Schematic Development for DC Motor and Motor Driver with STM uC | Completed
|  |  | DHT11 Sensor Intreface and functional Requirements | Completed
| Surya Prakash Singh | Hardware setup, Design, Integration | DHT11 Sensor Interface with uC | Completed
|  |  | DHT11 Circuit Connection, Flow Chart | Completed
|  |  | Photoresistor Circuit Connection and helping in hardware setup | Completed
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 0 | Completed
|  |  | Task assign., Helping in H/W Setup | Completed
|  |  | Photoresistor Interface with uC and connection of led bar. | Completed
|  |  | Photoresistor Interface and code development | Completed
|  |  | KeyPad Circuit Connection and managing tracker, Studying about the components. | Completed
| Vishawjeet Singh | Architecture, Hardware Setup, Design | LED Flasher Circuit Connection, Working of Led Flasher | Completed
|  |  | Functional Test of Photoresistor | Completed
|  |  | Integration of Photoresistor Sensor code with LED Flasher as per the algorithm | Completed
|  |  | Daily Scrum | Completed
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 3 | Completed
|  |  | Schematic Development for DHT11 Sensor with STM uC | Completed
|  |  | Schematic Development for Photoresistor with STM uC | Completed
|  |  | Complete Schematic Development | Completed
|  |  | Photoresistor Interface and functional Requirements | Completed

## Project_4
Project Start Date | 28/8/2025 | Project | Wearable Health Monitoring Device
Pune - Project-4 Status as on 16th September 2025
Team | Associates | Roles | Task | Status
TEAM 1 | Karishma BB | Software Design, Coding & Functional Testing, Debugging and Bug Fixing | Designed firmware architecture for 3 sensors data acquisition and processing. | Completed
|  |  | Implemented algorithms to calculate heart rate and SpO₂ from sensor inputs. | Completed
|  |  | Integrated ADC and digital I/O channels for real-time data collection. | Completed
|  |  | Wrote modular, reusable code for ease of maintenance and scalability. | In-Progress
|  |  | Conducted functional tests to ensure sensor accuracy and system responsiveness. | In-Progress
| Jayanth | Software Design, Coding & Unit Testing, Debugging and Bug Fixing | Developed communication protocols for data transfer to external devices. | Completed
|  |  | Programmed logic for threshold-based alerts and actuation triggers. | Completed
|  |  | Implemented keypad scanning and input validation routines. | Completed
|  |  | Created power management routines to optimize battery usage. | Completed
|  |  | Performed integration tests combining multiple modules for system reliability. | In-Progress
|  |  | Debugged cross-module interactions and ensured data consistency across outputs. | In-Progress
| Rahul Kumar Sharma & Sreenivas | Scrum Master, Documentation | Defined sprint goals and coordinated daily stand-ups to track progress. | Completed
|  |  | Assigned tasks and ensured timely delivery of milestones. | Completed
|  |  | Maintained version-controlled documentation for design and testing procedures. | Completed
|  |  | Prepared project reports and presentations for stakeholders. | Completed
|  |  | Facilitated team discussions to resolve technical challenges. | Completed
| Sri Kamesh Guru R | H/W Setup, Architect, Design | Designed circuit schematics integrating sensors, microcontroller, and output modules. | Completed
|  |  | Configured power supplies for stable voltage levels. | Completed
|  |  | Ensured proper interfacing between MPU6050, MAX30102, temperature sensor, and STM32F405. | Completed
|  |  | Assembled and tested hardware components on the development board. | Completed
|  |  | Verified signal integrity and sensor calibration under different operating conditions. | Completed
|  |  | Documented hardware setup for replication and troubleshooting. | Completed
| Aishwarya P | SiL Testing, Unit Testing, Integration Testing | Developed Software-in-the-Loop (SiL) test cases simulating real sensor inputs | In-Progress
|  |  | Automated unit tests to validate each software module independently. | In-Progress
|  |  | Designed test benches for sensor input verification and response accuracy. | In-Progress
|  |  | Ensured system stability across multiple test scenarios before deployment. | In-Progress
TEAM 2 | Kalpana P | Integration,Scrum Master,GIT HUB Management | Role distribution,Task allocation | Completed
|  |  | Combine hardware and software modules for full system operation. | Completed
|  |  | Building the test case for DS18B20 Sensor for temperature | Completed
|  |  | GITHUB MANAGEMENT | Completed
|  |  | Interfacing all the components | Completed
| Rambarath P | CODE,DEBUG,Integration,Unit testing | Unit Testing using CPP test | Completed
|  |  | Algorithm and flow chart for DS18B20 | Completed
|  |  | Algorithm and flow chart for MAX30102 sensor | Completed
|  |  | Interface DS18B20 with STM32 | Completed
|  |  | Debugging and Bug Fixing | Completed
|  |  | Keypad Control Code Development | Completed
| Kiruthigha R | ARCHITECT,DESIGN,H/W SETUP | Hardware Architecture and overview of the Hardware | Completed
|  |  | Circuit Diagram for MPU6050 accelerometer | Completed
|  |  | Algorithm and flow chart for MPU6050 accelerometer | Completed
|  |  | Circuit Diagram and flow for MAX30102 heart rate sensor | Completed
|  |  | Review,Reading Datasheet for pin confg | Completed
| Prasanthi T | Software Design,Documentation | Study of Hardware,Software | Completed
|  |  | Software Architecture and Discussed about MPU5060 Sensor | Completed
|  |  | Documentation | In-Progress
|  |  | Software Architecture and Discussed about MPU6050 accelerometer | Completed
Team 4 | Surya Prakash Singh | Coding & Unit Testing, Debugging and Bug Fixing | Implement sensor driver code for DHT11, MAX30100 in C/C++ using STM32 HAL. | Completed
|  |  | Write control logic for DC motor and buzzer activation based on sensor inputs. | Completed
|  |  | Develop modular code functions to ensure testability and reuse. | Completed
|  |  | Write unit tests using CppUTest for motor control and alert logic. | Completed
|  |  | Debug initialization and communication issues on STM32 pins. | Completed
|  |  | Fix bugs related to timing, sensor readings, or PWM signal behavior. | Completed
|  |  | Simulate edge cases like over-temperature or vibration to validate code. | Completed
|  |  | Refactor code based on feedback from integration and testing team. | Completed
|  |  | Maintain version control and commit tested modules to the repository. | Completed
|  |  | Provide weekly code status updates during scrum meetings. | Completed
| Ruban | Scrum Master, Documentation | Requirement Study and Prepare Story and TASK for ASSOCIATE 4 | Completed
|  |  | Algorithm and Flow Chart Development for DC Motor | Completed
|  |  | Flow Chart of LDR and Helping in H/W | Completed
|  |  | Schematic Development for DC Motor and Motor Driver with STM uC | Completed
|  |  | DHT11 Sensor Intreface and functional Requirements | Completed
| Anchal Dev | Hardware setup, Design, Integration | DHT11 Sensor Interface with uC | Completed
|  |  | DHT11 Circuit Connection, Flow Chart | Completed
|  |  | Photoresistor Circuit Connection and helping in hardware setup | Completed
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 0 | Completed
|  |  | Task assign., Helping in H/W Setup | Completed
|  |  | Photoresistor Interface with uC and connection of led bar. | Completed
|  |  | Photoresistor Interface and code development | Completed
|  |  | KeyPad Circuit Connection and managing tracker, Studying about the components. | Completed
| Vishawjeet Singh | Architecture, Hardware Setup, Design | LED Flasher Circuit Connection, Working of Led Flasher | Completed
|  |  | Functional Test of Photoresistor | Completed
|  |  | Integration of Photoresistor Sensor code with LED Flasher as per the algorithm | Completed
|  |  | Daily Scrum | Completed
|  |  | Requirement Study and Prepare Story and TASK for ASSOCIATE 3 | Completed
|  |  | Schematic Development for DHT11 Sensor with STM uC | Completed
|  |  | Schematic Development for Photoresistor with STM uC | Completed
|  |  | Complete Schematic Development | Completed
|  |  | Photoresistor Interface and functional Requirements | Completed
Team 3 | Anis Chelse N | Coding , Interfacing & Unit Testing | Requirement Study , Prepare Story for ASSOCIATE 1 | Completed
|  |  | Task assigning, Helping in H/W Setup | completed
|  |  | Code Development for Max3010 | Completed
|  |  | Keyboard code development | Completed
|  |  | Code Development for Mpu6050 | Completed
|  |  | Ingrating FreeRTOS and Interrupts | Completed
|  |  | Code Development for ds18b20 | Completed
Completed
| Surendhar | Architecture, Hardware setup, Design | Requirement Study and Prepare Story and TASK for ASSOCIATE 3 | Completed
|  |  | Schematic Development for Max3010 | Completed
|  |  | Schematic Development for Mpu6050 | Completed
|  |  | Schematic Development for ds18b20 | Completed
|  |  | Complete Schematic Development | Completed
|  |  | Hardware connection of Max3010 | Completed
|  |  | Hardware connection of Mpu6050 | Completed
|  |  | Hardware connection of ds18b20 | Completed
|  |  | Hardware connection of keyboard | Completed
Completed
| Dharsika | Debugging , Integration,Function Testing | Requirement Study and Prepare Story and TASK for ASSOCIATE 4 | Completed
|  |  | Max3010 Sensor functional Requirements | Completed
|  |  | Mpu6050 Interface functional Requirements | Completed
|  |  | ds18b20 functional Requirements | Completed
|  |  | keyboard functional Requirements | Completed
Completed
| Arun | Coding, Interfacing & Unit Testing , GIT Management | Requirement Study ,Prepare Story and TASK for ASSOCIATE 2 | Completed
|  |  | Installing GIT | Completed
|  |  | Creating a remote repository | Completed
|  |  | Making the initial push to the repository | Completed
|  |  | Overall flowchart for sensors | Completed
|  |  | Requirement Study and S/W architecture | Completed
Completed
| Deivanayaki | Debugging , Integration,Function Testing | Requirement Study and Prepare Story and TASK for ASSOCIATE 5 | Completed
|  |  | Max3010 Hardware requirements | Completed
|  |  | Mpu6050 Sensor HardwareRequirements | Completed
|  |  | ds18b20 Hardware requirements | Completed
|  |  | Integration of Complete Module | Completed
|  |  | Functional Test of Max3010 | Completed
|  |  | Functional Test of Mpu6050 | Completed
|  |  | Functional Test of ds18b20 | Completed
Completed
Completed

## Project_5
Project Start Date | 18/9/2025 | Project | Vehicle Health Monitoring System
Pune - Project-5 Status as on 30th September 2025
Team | Associates | Roles | Task | Status
TEAM 1 | Karishma BB | Software Design, Coding Debugging and Bug Fixing | Designed embedded software architecture for vehicle sensor data acquisition and diagnostics. | Completed
|  |  | Implemented algorithms for real-time monitoring of engine health, fuel efficiency, and emission levels. | Completed
|  |  | Designed software flow for integrating multiple vehicle health sensors | Completed
|  |  | Developed modular diagnostic routines for scalability and future vehicle model compatibility. | Completed
|  |  | Created modular and reusable code structure to simplify future updates and maintenance. | Completed
| Jayanth | Debugging , Integration,Function Testing | Performed unit testing using CPP test framework to validate modules. | Completed
|  |  | Debugged initialization issues and communication errors on STM32 pins. | Completed
|  |  | Fixed bugs related to timing mismatches and sensor readings. | Completed
|  |  | Created power optimization routines for vehicle’s electronic control unit (ECU). | Completed
|  |  | Performed unit testing of multi-sensor modules for accurate fault detection. | Completed
|  |  | Debugged cross-module interactions and ensured real-time data consistency across subsystems. | Completed
| Sreenivas | Scrum Master, Documentation | Defined sprint goals for phased development of the VHMS system. | Completed
|  |  | Coordinated daily scrums and progress tracking for timely deliverables. | Completed
|  |  | Maintained version-controlled documentation for diagnostics, and testing. | Completed
|  |  | Prepared technical reports and Presentation | Completed
|  |  | Facilitated discussions to resolve integration and safety compliance issues. | Completed
| Sri Kamesh Guru & Rahul Kumar Sharma | H/W Setup, Architect, Design | Designed circuit schematics integrating vehicle sensors (temperature, vibration, fuel). | Completed
|  |  | Configured stable power supply systems compatible with vehicle’s 12V/24V environment. | Completed
|  |  | Reviewing and reading datasheets for pin configurations. | Completed
|  |  | Built prototype hardware for real-time fault detection | Completed
|  |  | Conducted hardware-level test for multi sensors | Completed
|  |  | Optimized sensor placement to ensure accurate readings and minimal noise interference. | Completed
| Aiswarya P | Software Design, Coding Debugging and Bug Fixing | Designed embedded software architecture for vehicle sensor data acquisition and diagnostics. | Completed
|  |  | Implemented algorithms for real-time monitoring of engine health. | Completed
|  |  | Developed modular diagnostic routines for scalability and future vehicle model compatibility. | Completed
|  |  | Conducted functional tests to validate engine temperature,Human detection, accident detection | Completed
|  |  | Documentation and Presentation | Completed
TEAM 2 | Kiruthigha R | Scrum Master,GIT HUB Management,Integration | Role distribution,Task allocation | Completed
|  |  | Combine hardware and software modules for full system operation. | Completed
|  |  | circuit diagram and flow chart for DS18B20 temperature Sensor | Completed
|  |  | GITHUB MANAGEMENT | Completed
|  |  | Interfacing all the components | Completed
| Kalpana P | CODE,DEBUG,Unit testing | Unit Testing using CPP test | Completed
|  |  | Algorithm and flow chart for DHT11 temperature and Humidity Sensor | Completed
|  |  | Algorithm and flow chart for DHT11 sensor | Completed
|  |  | Interface DHT11 with STM32 | Completed
|  |  | Debug initialization and communication issues on STM32 pins. | Completed
|  |  | Fix bugs related to timing, sensor readings. | Completed
| Rambarath P | ARCHITECT,DESIGN,H/W SETUP | Hardware Architecture and overview of the Hardware | Completed
|  |  | Circuit Diagram for RFID R/W RC522 SPI S50 with RFID card and tag | Completed
|  |  | Algorithm and flow chart for RFID R/W RC522 SPI S50 with RFID card and tag | Completed
|  |  | Circuit Diagram and flow for IR sensor module | Completed
|  |  | Review,Reading Datasheet for pin config | Completed
| Prasanthi T | Software Design,Documentation | Study of Hardware,Software | Completed
|  |  | Software Architecture and Discussed about DS18B20 Sensor | Completed
|  |  | Circuit Diagram and flow for fuel level Sensor | Completed
|  |  | Documentation | In-Progress
|  |  | Software Architecture and Discussed about t Fuel level Sensor | Completed
|  |  | Documentation and Presentation | Completed
| Surya | H/W Setup, Architect, Design , Documentation | Implement sensor driver code for DS18B20 in C/C++ using STM32 HAL. | Completed
|  |  | Reviewing and reading datasheets for pin configurations. | Completed
|  |  | Built prototype hardware for real-time fault detection | Completed
|  |  | Prepared Presentation | In-Progress
|  |  | Study of Hardware | Completed
|  |  | Flow diagram of MPU 6050 | In-Progress
| Ruban | Debugging , Integration,Function Testing , JIRA management | Provide weekly code status updates during scrum meetings. | Completed
|  |  | Unit testing using Ceedling | Completed
|  |  | Manageing JIRA daily work process | Completed
|  |  | Intergration of all the sensors | In-Progress
|  |  | Fix bugs related to timing, sensor readings. | Completed
| Anchal Dev | Scrum Master, Documentation | Role distribution,Task allocation | Completed
|  |  | Combine hardware and software modules for full system operation. | Completed
|  |  | Coordinated daily scrums and progress tracking for timely deliverables. | Completed
|  |  | Maintained version-controlled documentation for diagnostics, and testing. | Completed
|  |  | Prepared technical reports and Presentation | In-Progress
| Vishawjeet Singh | Software Design, Coding , Architect , Documentation | Circuit Diagram and flow for fuel level Sensor | Completed
|  |  | Prepared technical reports | Completed
|  |  | Study of Hardware,Software | Completed
|  |  | Software Architecture and Discussed about Fuel level Sensor | Completed
|  |  | Implemented algorithms for real-time monitoring of engine health, fuel efficiency. | Completed
|  |  | Documentation and Presentation | Completed
Team 3 | Anis Chelse N | Scrum Master, unit Testing, integration testing | Requirement Study , Prepare Story for ASSOCIATE 1 | Completed
|  |  | Task assigning, Helping in H/W Setup | Completed
|  |  | Unit Test of all sensors | Completed
|  |  | Software Test Cases, Schematic Circuit diagram of project | Completed
|  |  | Integration of Complete Module | Completed
|  |  | Functional Test of Thermister | Completed
|  |  | Bug fixing and complete integration testing | Completed
| Surendhar | Coding, Fnuction testing, design | Requirement Study and Prepare Story and TASK for ASSOCIATE 3 | Completed
|  |  | Schematic Development for Mpu6050 | Completed
|  |  | Schematic Development for thermister | Completed
|  |  | Ingrating FreeRTOS and Interrupts | Completed
|  |  | Complete Schematic Development | Completed
|  |  | Hardware connection ofThermister | Completed
|  |  | Hardware connection of battery | Completed
|  |  | Hardware connection of water level sensor | Completed
| Dharsika | GIT management, Software coding | Requirement Study and Prepare Story and TASK for ASSOCIATE 4 | Completed
|  |  | Thermister Sensor functional Requirements | Completed
|  |  | Mpu6050 functional Requirements | Completed
|  |  | Installing GIT | Completed
|  |  | Creating a remote repository | Completed
|  |  | Making the initial push to the repository and version control | Completed
| Arun | Hardware setup, Documentation | Requirement Study ,Prepare Story and TASK for ASSOCIATE 2 | Completed
|  |  | Hardware Requirement Specifications | Completed
|  |  | UML diagrams usingVisual Paradigm | Completed
|  |  | Requirement Study and S/W architecture | Completed
|  |  | Overall flowchart for sensors | Completed
|  |  | Hardware connection of Mpu6050 | Completed
|  |  | Complete Schematic Development | In-Progress
| Deivanayaki | Hardware, Function testing , documentation | Requirement Study and Prepare Story and TASK for ASSOCIATE 5 | Completed
|  |  | RF ID Hardware requirements | Completed
|  |  | Mpu6050 Sensor HardwareRequirements | Completed
|  |  | Thermister Hardware requirements | Completed
|  |  | Hardware connection of water level sensor | Completed
|  |  | Software Requirement Specifications | Completed
|  |  | Functional Test of Mpu6050 | Completed
|  |  | Documentation and Presentation | Completed

## Project_6
| Project Start Date | 2025-08-10 | Project | Remote Controllerd Home Automation
Pune - Project-6 Status as on 15th October 2025
| Team | Associates | Roles | Task | Status
| TEAM 1 | Karishma BB | Software Design, Coding Debugging and Bug Fixing | Designed embedded software architecture for IR data acquisition and diagnostics. | Completed
|  |  |  | Implemented algorithms for real-time monitoring . | Completed
|  |  |  | Designed software flow for integration | Completed
|  |  |  | Developed modular diagnostic routines for scalability . | In-Progress
|  |  |  | Created modular and reusable code structure to simplify future updates and maintenance. | In-Progress
|  | Jayanth | Debugging , Integration,Function Testing | Performed unit testing using CPP test framework to validate modules. | Completed
|  |  |  | Debugged initialization issues and communication errors on STM32 pins. | Completed
|  |  |  | Fixed bugs related to timing mismatches and sensor readings. | Completed
|  |  |  | Created power optimization routines . | Completed
|  |  |  | Performed unit testing of multi-sensor modules . | In-Progress
|  |  |  | Debugged cross-module interactions and ensured real-time data consistency across subsystems. | In-Progress
|  | Sreenivas | Scrum Master, Documentation | Defined sprint goals for phased development . | Completed
|  |  |  | Coordinated daily scrums and progress tracking for timely deliverables. | In-Progress
|  |  |  | Maintained version-controlled documentation for diagnostics, and testing. | Yet to Start
|  |  |  | Prepared technical reports and Presentation | In-Progress
|  |  |  | Facilitated discussions to resolve integrations. | In-Progress
|  | Sri Kamesh Guru & Rahul Kumar Sharma | H/W Setup, Architect, Design | Designed schematics integrating sensors. | Completed
|  |  |  | Configured systems compatability | Completed
|  |  |  | Reviewing and reading datasheets for pin configurations. | Completed
|  |  |  | Built prototype hardware for real-time fault detection | In-Progress
|  |  |  | Conducted hardware-level test for multi sensors | In-Progress
|  |  |  | Optimized sensor placement to ensure accurate readings and minimal noise interference. | In-Progress
|  | Aiswarya P | Software Design, Coding Debugging and Bug Fixing | Designed embedded software architecture for IR data acquisition and diagnostics. | Completed
|  |  |  | Designed software flow for integration | Completed
|  |  |  | Developed modular diagnostic routines for scalability . | In-Progress
|  |  |  | Created modular and reusable code structure to simplify future updates and maintenance. | In-Progress
| TEAM 2 | Prasanthi T | Scrum Master,GIT HUB Management,Integration | Role distribution,Task allocation | Completed
|  |  |  | Combine hardware and software modules for full system operation. | Completed
|  |  |  | Implementing the motor driver and DC motor | Completed
|  |  |  | GITHUB MANAGEMENT,Documentation | Yet to Start
|  |  |  | Implementing the IR remote control and IR receiver module in manual mode | Completed
|  | Rambarath P | CODE,DEBUG,Unit testing | Unit Testing using CPP test | Completed
|  |  |  | Algorithm and flow chart for IR remote control and IR receiver module | Completed
|  |  |  | Debug initialization and communication issues on STM32 pins. | Completed
|  |  |  | Fix bugs related to timing, sensor readings. | Yet to Start
|  | Kalpana P | ARCHITECT,DESIGN,H/W SETUP | Hardware Architecture and overview of the Hardware | Completed
|  |  |  | Circuit Diagram for relay with DC LED bulb | Completed
|  |  |  | Algorithm and flow chart for Controlling Lights using UART Messages | In-Progress
|  |  |  | Review,Reading Datasheet for pin config | Completed
|  | Kiruthigha R | Software Design,Documentation | Study of Hardware,Software | Completed
|  |  |  | Software Architecture and Discussed about UART | In-Progress
|  |  |  | Circuit Diagram for Controlling Fan using UART Messages | In-Progress
|  |  |  | Algorithm and flow chart for Controlling Fan using UART Messages | In-Progress
|  | Surya | H/W Setup, Architect, Design , Documentation | Implement sensor driver code for DC LIGHT BULB in C/C++ using STM32 HAL. | Completed
|  |  |  | Reviewing and reading datasheets for pin configurations. | Completed
|  |  |  | Built prototype hardware for real-time fault detection | In-Progress
|  |  |  | Prepared Presentation | Completed
|  |  |  | Study of Hardware | Completed
|  |  |  | Flow diagram management | Yet to start
|  | Ruban | Debugging , Integration,Function Testing , JIRA management | Provide weekly code status updates during scrum meetings. | Completed
|  |  |  | Unit testing using Ceedling | In-Progress
|  |  |  | Manageing JIRA daily work process | Completed
|  |  |  | Intergration of all the sensors | In-Progress
|  |  |  | Fix bugs related to timing, sensor readings. | Completed
|  | Anchal Dev | Scrum Master, Documentation,S/W setup(Remotely available) | Role distribution,Task allocation | Completed
|  |  |  | Combine hardware and software modules for full system operation. | Completed
|  |  |  | Coordinated daily scrums and progress tracking for timely deliverables. | Completed
|  |  |  | Maintained version-controlled documentation for diagnostics, and testing. | Completed
|  |  |  | Prepared technical reports and Presentation | In-Progress
|  | Vishawjeet Singh | Software Design, Coding , Architect , Documentation | Circuit Diagram and flow for Tempearture Measuremtent & DC Motor | Completed
|  |  |  | Prepared technical reports | Completed
|  |  |  | Study of Hardware,Software | Completed
|  |  |  | Software Architecture and Discussed about | Completed
|  |  |  | Implemented algorithms for real-time monitoring of engine health, fuel efficiency. | Completed
| Team 3 | Anis Chelse N | Hardware Setup, Architect, Design, GIT Management | IR sensor module Study | Completed
|  |  |  | Hardware Requirement Specifications Documentation | Completed
|  |  |  | GIT repository creation | Completed
|  |  |  | Prepared UML diagrams | Completed
|  |  |  | Hardware Interfacing | In-Progress
|  | Surendhar | Software Design, Scrum Master | Role distribution,Task allocation | Completed
|  |  |  | Daily Scrums and Progress tracking | Completed
|  |  |  | Working with Motor Driver module | Completed
|  |  |  | Intregrating DC motor with Motor Driver module | Completed
|  |  |  | Integrating LED & Relay Modules | Completed
I |  |  |  | Interfacing the commands for the Lights and FAN | In-Progress
|  | Dharsika | Hardware Design, Architect | Requirements Specification Documentation | Completed
|  |  |  | Motor Driver Module Study | Completed
|  |  |  | Flow chart, Circuit diagram Preparation | In-Progress
|  |  |  | Pin configuration checking | In-Progress
|  | Arun | Unit & Functional Testing, Documentation | Preparing Hardware Test cases documentation | Completed
|  |  |  | Preparing Software Test cases documentation | Completed
|  |  |  | Unit testing the Motor driver module | Completed
|  |  |  | Functional and integration testing | In-Progress
|  |  |  | Test report documentation | Yet to Start
|  | Deivanayaki | Software Design, Documentation | Interfacing Manual override buttons | Completed
|  |  |  | Agile Daily tracking | In-Progress
|  |  |  | Interfacing LED and Relay module | In-Progress
|  |  |  | Report Documentation | Yet to Start

## Project_7
| Project Start Date | 29/10/2025 | Project | Vehicle Time Management
Pune - Project-7 Status as on October 2025
| Team | Associates | Roles | Task | Status
| TEAM 1 | Karishma BB | Software Design, Coding Debugging and Bug Fixing | Designed embedded software architecture for IR data acquisition and diagnostics. | Completed
|  |  |  | Implemented algorithms for real-time monitoring . | Completed
|  |  |  | Designed software flow for integration | Completed
|  |  |  | Developed modular diagnostic routines for scalability . | In-Progress
|  |  |  | Created modular and reusable code structure to simplify future updates and maintenance. | In-Progress
|  | Jayanth | Debugging , Integration,Function Testing | Performed unit testing using CPP test framework to validate modules. | Completed
|  |  |  | Debugged initialization issues and communication errors on STM32 pins. | Completed
|  |  |  | Fixed bugs related to timing mismatches and sensor readings. | Completed
|  |  |  | Created power optimization routines . | Completed
|  |  |  | Performed unit testing of multi-sensor modules . | In-Progress
|  |  |  | Debugged cross-module interactions and ensured real-time data consistency across subsystems. | In-Progress
|  | Sreenivas | Scrum Master, Documentation | Defined sprint goals for phased development . | Completed
|  |  |  | Coordinated daily scrums and progress tracking for timely deliverables. | In-Progress
|  |  |  | Maintained version-controlled documentation for diagnostics, and testing. | Yet to Start
|  |  |  | Prepared technical reports and Presentation | In-Progress
|  |  |  | Facilitated discussions to resolve integrations. | In-Progress
|  | Sri Kamesh Guru & Rahul Kumar Sharma | H/W Setup, Architect, Design | Designed schematics integrating sensors. | Completed
|  |  |  | Configured systems compatability | Completed
|  |  |  | Reviewing and reading datasheets for pin configurations. | Completed
|  |  |  | Built prototype hardware for real-time fault detection | In-Progress
|  |  |  | Conducted hardware-level test for multi sensors | In-Progress
|  |  |  | Optimized sensor placement to ensure accurate readings and minimal noise interference. | In-Progress
|  | Aiswarya P | Software Design, Coding Debugging and Bug Fixing | Designed embedded software architecture for IR data acquisition and diagnostics. | Completed
|  |  |  | Designed software flow for integration | Completed
|  |  |  | Developed modular diagnostic routines for scalability . | In-Progress
|  |  |  | Created modular and reusable code structure to simplify future updates and maintenance. | In-Progress
| TEAM 2 | Prasanthi T | Scrum Master,GIT HUB Management,Integration | Role distribution,Task allocation | Completed
|  |  |  | Combine hardware and software modules for full system operation. | Completed
|  |  |  | Implementing the motor driver and DC motor | Completed
|  |  |  | GITHUB MANAGEMENT,Documentation | Yet to Start
|  |  |  | Implementing the IR remote control and IR receiver module in manual mode | Completed
|  | Rambarath P | CODE,DEBUG,Unit testing | Unit Testing using CPP test | Completed
|  |  |  | Algorithm and flow chart for IR remote control and IR receiver module | Completed
|  |  |  | Debug initialization and communication issues on STM32 pins. | Completed
|  |  |  | Fix bugs related to timing, sensor readings. | Yet to Start
|  | Kalpana P | ARCHITECT,DESIGN,H/W SETUP | Hardware Architecture and overview of the Hardware | Completed
|  |  |  | Circuit Diagram for relay with DC LED bulb | Completed
|  |  |  | Algorithm and flow chart for Controlling Lights using UART Messages | In-Progress
|  |  |  | Review,Reading Datasheet for pin config | Completed
|  | Kiruthigha R | Software Design,Documentation | Study of Hardware,Software | Completed
|  |  |  | Software Architecture and Discussed about UART | In-Progress
|  |  |  | Circuit Diagram for Controlling Fan using UART Messages | In-Progress
|  |  |  | Algorithm and flow chart for Controlling Fan using UART Messages | In-Progress
|  | Surya | H/W Setup, Architect, Design , Documentation | Implement sensor driver code for DC LIGHT BULB in C/C++ using STM32 HAL. | Completed
|  |  |  | Reviewing and reading datasheets for pin configurations. | Completed
|  |  |  | Built prototype hardware for real-time fault detection | In-Progress
|  |  |  | Prepared Presentation | Completed
|  |  |  | Study of Hardware | Completed
|  |  |  | Flow diagram management | Yet to start
|  | Ruban | Debugging , Integration,Function Testing , JIRA management | Provide weekly code status updates during scrum meetings. | Completed
|  |  |  | Unit testing using Ceedling | In-Progress
|  |  |  | Manageing JIRA daily work process | Completed
|  |  |  | Intergration of all the sensors | In-Progress
|  |  |  | Fix bugs related to timing, sensor readings. | Completed
|  | Anchal Dev | Scrum Master, Documentation,S/W setup(Remotely available) | Role distribution,Task allocation | Completed
|  |  |  | Combine hardware and software modules for full system operation. | Completed
|  |  |  | Coordinated daily scrums and progress tracking for timely deliverables. | Completed
|  |  |  | Maintained version-controlled documentation for diagnostics, and testing. | Completed
|  |  |  | Prepared technical reports and Presentation | In-Progress
|  | Vishawjeet Singh | Software Design, Coding , Architect , Documentation | Circuit Diagram and flow for Tempearture Measuremtent & DC Motor | Completed
|  |  |  | Prepared technical reports | Completed
|  |  |  | Study of Hardware,Software | Completed
|  |  |  | Software Architecture and Discussed about | Completed
|  |  |  | Implemented algorithms for real-time monitoring of engine health, fuel efficiency. | Completed
| Team 3 | Anis Chelse N | Hardware Setup, Architect, Design, GIT Management | IR sensor module Study | Completed
|  |  |  | Hardware Requirement Specifications Documentation | Completed
|  |  |  | GIT repository creation | Completed
|  |  |  | Prepared UML diagrams | Completed
|  |  |  | Hardware Interfacing | In-Progress
|  | Surendhar | Software Design, Scrum Master | Role distribution,Task allocation | Completed
|  |  |  | Daily Scrums and Progress tracking | Completed
|  |  |  | Working with Motor Driver module | Completed
|  |  |  | Intregrating DC motor with Motor Driver module | Completed
|  |  |  | Integrating LED & Relay Modules | Completed
I |  |  |  | Interfacing the commands for the Lights and FAN | In-Progress
|  | Dharsika | Hardware Design, Architect | Requirements Specification Documentation | Completed
|  |  |  | Motor Driver Module Study | Completed
|  |  |  | Flow chart, Circuit diagram Preparation | In-Progress
|  |  |  | Pin configuration checking | In-Progress
|  | Arun | Unit & Functional Testing, Documentation | Preparing Hardware Test cases documentation | Completed
|  |  |  | Preparing Software Test cases documentation | Completed
|  |  |  | Unit testing the Motor driver module | Completed
|  |  |  | Functional and integration testing | In-Progress
|  |  |  | Test report documentation | Yet to Start
|  | Deivanayaki | Software Design, Documentation | Interfacing Manual override buttons | Completed
|  |  |  | Agile Daily tracking | In-Progress
|  |  |  | Interfacing LED and Relay module | In-Progress
|  |  |  | Report Documentation | Yet to Start